## Sheet1
Task | Owner (Squad Role) | Start Date | Duration (Days) | Phase
Phase 1: Foundation | Cloud Architect | 2026-01-20 | 60 | Foundation
Phase 2: Logic & Agents | AI Engineer | 2026-02-20 | 60 | Logic & Agents
Phase 3: Resilience | DevOps / SRE | 2026-03-20 | 60 | Resilience
Phase 4: End-User HITL | Frontend Dev | 2026-04-20 | 60 | HITL
Phase 5: Production Rollout | Whole Squad | 2026-05-20 | 30 | Run Phase
Start Date | 46042

## Sheet2
Month | Phase | Active Users (MAU) | Fixed Infra Baseline | Scaling Infra Cost | LLM Token Cost | Total Monthly OpEx
M1 | Foundation/Pilot | 500 | 2370 | 200 | 3850 | 6420
M2 | Early Adopters | 1000 | 2370 | 400 | 7700 | 10470
M3 | Scaling (L3/Ops) | 2500 | 2370 | 1000 | 19250 | 22620
M4 | Expansion | 5000 | 2370 | 20000 | 38500 | 60870
M5 | Majority Rollout | 10000 | 2370 | 4050 | 51000 | 57420
M6 | Full Adoption | 18000 | 2370 | 7250 | 73500 | 83120
M7 | Retention/Opt. | 22000 | 2370 | 8900 | 89800 | 101070
M8 | Steady State | 25000 | 2370 | 10100 | 102000 | 114470
[7 empty] | Service Category | Estimated Cost | Core Purpose & Governance
[7 empty] | Confidential Compute | 800 | Management fee for GKE Autopilot and the minimum "warm" pods for the LangGraph Supervisor. Includes the premium for RAM Encryption.
[7 empty] | Knowledge Search Index | 600 | Continuous hosting of the Vertex AI Search vector store to ensure RAG data (Confluence/Drive) is instantly available.
[7 empty] | Stateful Data Tier | 250 | Cloud SQL (HA) instance for stateful multi-agent checkpointing, ensuring conversation continuity.
[7 empty] | Networking & LB | 470 | Global External HTTP(S) LB with US-based Anycast IP and cross-region data transfer
[7 empty] | Security & Perimeter | 250 | Fixed costs for VPC Service Controls, IAP Authentication, Cloud NAT, and Secret Manager.
[7 empty] | TOTAL BASELINE | 2370 | Minimum "Sovereign Tax" for a Zero-Trust Enclave.